## 1. Exec Dashboard
FIRE FIGHTING SYSTEM — NEW DC
Installation Schedule & Project Responsibility Tracker
Survey Date: 30-Jun-2026 ¦ PM: Kharsan Mujeb Al Ajmi ¦ [OFFICIAL LOGO — TO BE INSERTED]
PROPOSED PLANNING BASELINE — Proposed planning dates are preliminary and subject to confirmation by the Project Owner, PM, Contractor and relevant stakeholders. Only items marked CONFIRMED (SURVEY) are supported by the source report.
EXECUTIVE SUMMARY
| Project |  |  |  | Fire Fighting System for New DC
| Location / Asset |  |  |  | Mobile / Trailer-based DC
| Survey Date |  |  |  | 30-Jun-2026
| Project Manager |  |  |  | Kharsan Mujeb Al Ajmi
| Source Document |  |  |  | RC Vehicle Survey Report – Fire Fighting System for New DC
| Recommended Systems |  |  |  | Fire Alarm System · Fire Suppression System
| Current Situation |  |  |  | Per the RC Vehicle Survey Report dated 30-Jun-2026: installation of Racks and Cabinets has not yet started in the available trailers, and the power source in Trailer-2 is currently unavailable because partition works are still ongoing. The survey recommends providing a Fire Alarm System and a Fire Suppression System. No installation start, duration or completion dates are stated in the source document.
| Overall Status |  |  |  | PLANNING / SITE READINESS PENDING
KEY PERFORMANCE INDICATORS — calculated live from the Master Schedule
| TOTAL ACTIVITIES |  |  | COMPLETED |  | IN PROGRESS |  | BLOCKED |  |  | NOT STARTED |  | OVERALL COMPLETE
| 49 |  |  | 1 |  | 1 |  | 2 |  |  | 41 |  | 2.041%
| Across 6 phases |  |  | Confirmed by survey |  | Partition works ongoing |  | Trailer-2 power |  |  | Awaiting site readiness |  | Weighted equally
CRITICAL CONSTRAINTS — confirmed by the survey
| CONSTRAINT 01 · RACKS & CABINETS | [6 empty] | CONSTRAINT 02 · TRAILER-2 POWER
| Installation of Racks and Cabinets has not yet started in the available trailers. | [6 empty] | The power source in Trailer-2 is currently unavailable because partition works are still ongoing.
| Impact: gates fire alarm and suppression activities that interface with racks and cabinets (4.01, 4.04, 4.07) and therefore the whole installation phase. Required action: confirm scope, contractor and start date (Action A03). Responsible: Main Contractor (TBC) Target resolution: TBD | [6 empty] | Impact: blocks power availability verification (2.02) and power and control connections (4.08); gates functional testing (5.05) and Trailer-2 handover. Required action: complete partition works, then verify and energise (Actions A01, A02). Responsible: Civil / Partition Contractor (TBC) → Electrical Contractor (TBC) Target resolution: TBD
KEY MILESTONES
| Milestone |  |  |  | Target Date | Owner | Status |  | Dependency |  |  | Remarks
| Project Kickoff |  |  |  | TBD | TBC | Not Started |  | Stakeholder confirmation |  |  | Baseline agreement and governance sign-off.
| Site Readiness Confirmed |  |  |  | TBD | TBC | Not Started |  | Partition works + installation area verification |  |  | Gate for all site activities.
| Power Available (Trailer-2) |  |  |  | TBD | TBC | Blocked |  | Completion of partition works |  |  | CONFIRMED constraint: Trailer-2 power source currently unavailable.
| Racks & Cabinets Ready |  |  |  | TBD | TBC | Not Started |  | Installation of Racks and Cabinets (2.04) |  |  | CONFIRMED constraint: installation has not yet started.
| Engineering Approved |  |  |  | TBD | TBC | Pending Approval |  | Shop drawing and material approval (3.05) |  |  | Approving authority to be confirmed.
| Materials Available on Site |  |  |  | TBD | TBC | Pending Material |  | Procurement and delivery (3.06 / 3.07) |  |  | Lead times unknown until equipment selection is confirmed.
| Installation Start |  |  |  | TBD | TBC | Not Started |  | M02 + M04 + M06 |  |  | Cannot start before all three readiness gates close.
| Installation Complete |  |  |  | TBD | TBC | Not Started |  | System integration (4.09) |  |  | Includes power and control connections.
| Testing Complete |  |  |  | TBD | TBC | Not Started |  | Integration testing (5.06) |  |  | Both recommended systems tested.
| Defects Closed |  |  |  | TBD | TBC | Not Started |  | Rectification and retesting (5.08 / 5.09) |  |  | Zero open critical defects.
| Final Acceptance |  |  |  | TBD | TBC | Not Started |  | Final acceptance and sign-off (6.07) |  |  | Acceptance criteria to be agreed at kickoff.
| Handover |  |  |  | TBD | TBC | Not Started |  | System handover to operations (6.08) |  |  | Handover certificate issued.
| Project Closeout |  |  |  | TBD | TBC | Not Started |  | Project closeout (6.09) |  |  | Overall project completion date TBD.
MANAGEMENT ATTENTION — critical path actions
| Action ID |  | Required Action |  |  |  | Responsible |  |  | Priority |  | Status | Escalation / Remarks
| A01 |  | Complete partition works in Trailer-2 |  |  |  | Civil / Partition Contractor (TBC) |  |  | Critical |  | In Progress | CRITICAL PATH — first link in the Trailer-2 readiness chain.
| A02 |  | Confirm power availability in Trailer-2 once partitions are complete |  |  |  | Electrical Contractor (TBC) |  |  | Critical |  | Blocked | CRITICAL PATH — gates power and control connections and functional testing.
| A03 |  | Start and complete installation of Racks and Cabinets |  |  |  | Main Contractor (TBC) |  |  | Critical |  | Not Started | CRITICAL PATH — gates all rack/cabinet-interfacing fire system works.
| A04 |  | Confirm overall site readiness and release installation work fronts |  |  |  | Project Manager — Kharsan Mujeb Al Ajmi |  |  | Critical |  | Not Started | Sequence: A01 → A02 → A03 → A04 → release Phase 4.
| A05 |  | Nominate the Project Owner and confirm the governance structure |  |  |  | Project Manager — Kharsan Mujeb Al Ajmi |  |  | High |  | Not Started | Required before any approval-gated activity can complete.
| A06 |  | Appoint the Main Contractor and Fire System Contractor |  |  |  | Project Owner (TBC) |  |  | High |  | Not Started | Required to resource Phases 2 to 6.
STATUS KEY & DOCUMENT LEGEND
| 🟢 | Completed / On Track |  |  |  |  | 🟡 | At Risk / Pending
| 🔴 | Blocked / Critical |  |  |  |  | ⚪ | Not Started
| 🔵 | In Progress |  |  |  |  | ▨ | Shaded cell = editable field for the project team
CONFIRMED INFORMATION FROM SURVEY is limited to: project and location, survey date 30-Jun-2026, Project Manager Kharsan Mujeb Al Ajmi, the two site constraints above, and the recommendation to provide a Fire Alarm System and a Fire Suppression System. Everything else in this workbook is a PROPOSED PLANNING BASELINE or marked TBC / TBD.
Confidential — Project Planning Document · Prepared based on the RC Vehicle Survey Report dated 30-Jun-2026 · Version 0.1 — Preliminary Planning Baseline · Last updated: TBC

## 2. Master Schedule
FIRE FIGHTING SYSTEM — NEW DC
Installation Schedule & Project Responsibility Tracker
Survey Date: 30-Jun-2026 ¦ PM: Kharsan Mujeb Al Ajmi ¦ [OFFICIAL LOGO — TO BE INSERTED]
PROPOSED PLANNING BASELINE — Proposed planning dates are preliminary and subject to confirmation by the Project Owner, PM, Contractor and relevant stakeholders. Only items marked CONFIRMED (SURVEY) are supported by the source report.
HOW TO USE · Shaded input cells (Planned Start / Planned Finish / % Complete) and blue text are for the project team to complete. · Duration, Days Remaining and Schedule Flag calculate automatically. · Status is a drop-down list. · Remarks tagged “CONFIRMED (SURVEY)” are supported by the source report; everything else is a proposed planning value or TBC.
ID | WBS | Phase | Activity | Trailer / Location | Prede- cessor | Planned Start (enter date) | Planned Finish (enter date) | Duration (days) | Status | % Complete | Responsible Person | Role | Project Owner | Contractor | Dependency | Risk / Blocker | Approval Required | Remarks | Days Remaining (auto) | Schedule Flag (auto)
Phase 1 — Project Preparation · Proposed baseline: Week 1 – Week 2
1 | 1.01 | Phase 1 — Project Preparation | Project kickoff meeting and baseline agreement | All trailers | — |  |  | TBD | Not Started | 0% | Kharsan Mujeb Al Ajmi | Project Manager | TBC | TBC | Stakeholder availability | — | No | Kickoff to confirm scope, team, baseline dates and reporting cycle. | TBD | ON PLAN
2 | 1.02 | Phase 1 — Project Preparation | Site survey execution — RC Vehicle Survey | Mobile / Trailer-based DC | — | 2026-06-30 | 2026-06-30 | 1 | Completed | 100% | TBC | Survey Team | TBC | TBC | — | — | No | CONFIRMED (SURVEY): Survey carried out and reported on 30-Jun-2026. Completed prior to this baseline. | Closed | COMPLETE
3 | 1.03 | Phase 1 — Project Preparation | Review of RC Vehicle Survey Report dated 30-Jun-2026 | All trailers | 1.02 |  |  | TBD | Ready to Start | 0% | Kharsan Mujeb Al Ajmi | Project Manager | TBC | TBC | Survey report issued (1.02 complete) | — | No | Source document is available; formal team review not yet recorded. | TBD | READY TO START
4 | 1.04 | Phase 1 — Project Preparation | Scope confirmation — Fire Alarm System and Fire Suppression System | All trailers | 1.03 |  |  | TBD | Not Started | 0% | Kharsan Mujeb Al Ajmi | Project Manager | TBC | TBC | Survey report review complete | — | Yes | CONFIRMED (SURVEY): Survey recommends providing a Fire Alarm System and a Fire Suppression System. | TBD | PENDING PREDECESSOR
5 | 1.05 | Phase 1 — Project Preparation | Confirmation of project stakeholders, owner and governance | N/A | 1.01 |  |  | TBD | Not Started | 0% | Kharsan Mujeb Al Ajmi | Project Manager | TBC | TBC | Project Owner nomination | Project Owner not yet identified | Yes | Project Owner, Main Contractor, Fire System Contractor and Client Rep to be named. | TBD | PENDING PREDECESSOR
6 | 1.06 | Phase 1 — Project Preparation | Site readiness verification walkdown | All trailers | 1.04 |  |  | TBD | Not Started | 0% | TBC | Site Supervisor | TBC | TBC | Scope confirmed | Site not yet ready — see Phase 2 | No | Joint walkdown to baseline actual readiness against survey findings. | TBD | PENDING PREDECESSOR
7 | 1.07 | Phase 1 — Project Preparation | Confirmation of trailer availability | All trailers | 1.06 |  |  | TBD | Not Started | 0% | Kharsan Mujeb Al Ajmi | Project Manager | TBC | TBC | Walkdown complete | — | No | Number and identity of trailers released for installation to be confirmed. | TBD | PENDING PREDECESSOR
8 | 1.08 | Phase 1 — Project Preparation | Confirmation of installation areas within trailers | All trailers | 1.07 |  |  | TBD | Not Started | 0% | TBC | Fire & Life Safety Engineer | TBC | TBC | Trailer availability confirmed | — | No | Installation areas to be agreed once partitions and rack layout are fixed. | TBD | PENDING PREDECESSOR
Phase 2 — Civil / Site Readiness · Proposed baseline: Week 1 – Week 6
9 | 2.01 | Phase 2 — Civil / Site Readiness | Completion of partition works | Trailer-2 | — |  |  | TBD | In Progress | 0% | TBC | Civil / Partition Contractor | TBC | TBC | Civil works front | Ongoing partition works block power availability | No | CONFIRMED (SURVEY): Partition works are still ongoing in Trailer-2. Completion date and % progress TBC. | TBD | IN PROGRESS
10 | 2.02 | Phase 2 — Civil / Site Readiness | Power source availability verification and energisation | Trailer-2 | 2.01 |  |  | TBD | Blocked | 0% | TBC | Electrical Contractor | TBC | TBC | Completion of partition works + Power availability confirmation | Trailer-2 power source currently unavailable | Yes | CONFIRMED (SURVEY): Power source in Trailer-2 is currently unavailable because partition works are ongoing. | TBD | BLOCKED
11 | 2.03 | Phase 2 — Civil / Site Readiness | Verification of available installation areas | All trailers | 1.08 |  |  | TBD | Not Started | 0% | TBC | Site Supervisor | TBC | TBC | Installation areas confirmed | — | No | Physical verification of clear areas for alarm and suppression equipment. | TBD | PENDING PREDECESSOR
12 | 2.04 | Phase 2 — Civil / Site Readiness | Installation of Racks and Cabinets | All trailers | 2.03 |  |  | TBD | Not Started | 0% | TBC | Main Contractor | TBC | TBC | Installation areas verified | Racks and Cabinets installation not yet started | No | CONFIRMED (SURVEY): Installation of Racks and Cabinets has not yet started in the available trailers. | TBD | PENDING PREDECESSOR
13 | 2.05 | Phase 2 — Civil / Site Readiness | Racks and Cabinets readiness confirmation / sign-off | All trailers | 2.04 |  |  | TBD | Not Started | 0% | TBC | QA/QC | TBC | TBC | Racks and Cabinets installation complete | Racks and Cabinets not yet started | Yes | Gate for all rack/cabinet-interfacing fire system activities. | TBD | PENDING PREDECESSOR
14 | 2.06 | Phase 2 — Civil / Site Readiness | Power availability verification — trailers other than Trailer-2 | All trailers | 1.07 |  |  | TBD | Not Started | 0% | TBC | Electrical Contractor | TBC | TBC | Trailer availability confirmed | Survey confirms unavailability for Trailer-2 only; other trailers to be verified | No | Source confirms the power constraint for Trailer-2. Status of remaining trailers TBC. | TBD | PENDING PREDECESSOR
15 | 2.07 | Phase 2 — Civil / Site Readiness | Access, HSE induction and work permit readiness | All trailers | 1.01 |  |  | TBD | Not Started | 0% | TBC | HSE | TBC | TBC | Kickoff complete | — | Yes | Permit-to-work regime, hot work and access control to be established. | TBD | PENDING PREDECESSOR
Phase 3 — Engineering & Material Readiness · Proposed baseline: Week 2 – Week 8
16 | 3.01 | Phase 3 — Engineering & Material Readiness | Fire suppression system design review | All trailers | 1.04 |  |  | TBD | Not Started | 0% | TBC | Fire Suppression Engineer | TBC | TBC | Scope confirmed | — | No | Design basis, agent type and coverage to be confirmed during engineering/design. | TBD | PENDING PREDECESSOR
17 | 3.02 | Phase 3 — Engineering & Material Readiness | Fire alarm system design review | All trailers | 1.04 |  |  | TBD | Not Started | 0% | TBC | Fire Alarm Engineer | TBC | TBC | Scope confirmed | — | No | Detection philosophy and panel architecture to be confirmed during engineering/design. | TBD | PENDING PREDECESSOR
18 | 3.03 | Phase 3 — Engineering & Material Readiness | Equipment and material confirmation | All trailers | 3.01 |  |  | TBD | Not Started | 0% | TBC | Fire System Specialist | TBC | TBC | Design reviews complete | — | No | Equipment types not specified in the survey — to be confirmed during engineering/design. | TBD | PENDING PREDECESSOR
19 | 3.04 | Phase 3 — Engineering & Material Readiness | Shop drawing and technical submittal preparation | All trailers | 3.03 |  |  | TBD | Not Started | 0% | TBC | Fire System Specialist | TBC | TBC | Material list confirmed | — | No | Submittal package covering both recommended systems. | TBD | PENDING PREDECESSOR
20 | 3.05 | Phase 3 — Engineering & Material Readiness | Shop drawing and material approval | All trailers | 3.04 |  |  | TBD | Pending Approval | 0% | TBC | Client Representative | TBC | TBC | Submittal issued | Approval turnaround not yet agreed | Yes | Approving authority and review duration to be confirmed. | TBD | PENDING PREDECESSOR
21 | 3.06 | Phase 3 — Engineering & Material Readiness | Procurement and purchase order release | All trailers | 3.05 |  |  | TBD | Pending Material | 0% | TBC | Main Contractor | TBC | TBC | Material approval obtained | Long-lead items may drive the critical path | Yes | Lead times unknown until equipment selection is confirmed. | TBD | PENDING PREDECESSOR
22 | 3.07 | Phase 3 — Engineering & Material Readiness | Manufacturing, delivery to site and material inspection | All trailers | 3.06 |  |  | TBD | Pending Material | 0% | TBC | Main Contractor | TBC | TBC | Purchase orders placed | Delivery lead time TBC | No | Material availability is a gate for the start of Phase 4. | TBD | PENDING PREDECESSOR
Phase 4 — Installation · Proposed baseline: Week 8 – Week 12
23 | 4.01 | Phase 4 — Installation | Fire alarm system installation — containment and cabling | All trailers | 3.07 |  |  | TBD | Not Started | 0% | TBC | Fire System Specialist | TBC | TBC | Material on site + Racks and Cabinets ready (2.05) | Racks and Cabinets installation not yet started | No | First installation front; cannot start before site readiness gates are closed. | TBD | PENDING PREDECESSOR
24 | 4.02 | Phase 4 — Installation | Fire detection devices installation | All trailers | 4.01 |  |  | TBD | Not Started | 0% | TBC | Fire Alarm Engineer | TBC | TBC | Containment and cabling complete | — | No | Device types to be confirmed during engineering/design. | TBD | PENDING PREDECESSOR
25 | 4.03 | Phase 4 — Installation | Fire alarm control and monitoring equipment installation | All trailers | 4.01 |  |  | TBD | Not Started | 0% | TBC | Fire Alarm Engineer | TBC | TBC | Containment and cabling complete | — | No | Control/monitoring equipment scope to be confirmed during engineering/design. | TBD | PENDING PREDECESSOR
26 | 4.04 | Phase 4 — Installation | Fire suppression system installation — mounting and supports | All trailers | 3.07 |  |  | TBD | Not Started | 0% | TBC | Fire Suppression Engineer | TBC | TBC | Material on site + Racks and Cabinets ready (2.05) | Racks and Cabinets installation not yet started | No | Suppression system recommended by the survey; configuration TBC in design. | TBD | PENDING PREDECESSOR
27 | 4.05 | Phase 4 — Installation | Suppression equipment installation | All trailers | 4.04 |  |  | TBD | Not Started | 0% | TBC | Fire Suppression Engineer | TBC | TBC | Mounting and supports complete | — | No | Equipment types to be confirmed during engineering/design. | TBD | PENDING PREDECESSOR
28 | 4.06 | Phase 4 — Installation | Piping / tubing and associated components installation (where applicable) | All trailers | 4.05 |  |  | TBD | Not Started | 0% | TBC | Fire Suppression Engineer | TBC | TBC | Suppression equipment installed | — | No | Applicability depends on the suppression solution confirmed during design. | TBD | PENDING PREDECESSOR
29 | 4.07 | Phase 4 — Installation | Interfaces with racks and cabinets | All trailers | 2.05 |  |  | TBD | Not Started | 0% | TBC | Fire System Specialist | TBC | TBC | Racks and Cabinets ready (2.05) | Racks and Cabinets installation not yet started | No | Directly gated by the rack/cabinet readiness constraint recorded in the survey. | TBD | PENDING PREDECESSOR
30 | 4.08 | Phase 4 — Installation | Power and control connections | Trailer-2 / All trailers | 2.02 |  |  | TBD | Blocked | 0% | TBC | Electrical Contractor | TBC | TBC | Completion of partition works + Power availability confirmation (Trailer-2) | Trailer-2 power source currently unavailable | No | CONFIRMED (SURVEY): Cannot proceed in Trailer-2 until partition works finish and power is available. | TBD | BLOCKED
31 | 4.09 | Phase 4 — Installation | System integration — fire alarm and fire suppression | All trailers | 4.08 |  |  | TBD | Not Started | 0% | TBC | Fire & Life Safety Engineer | TBC | TBC | Power and control connections complete | Dependent on Trailer-2 power availability | No | Integration scope with DC systems to be confirmed during design. | TBD | PENDING PREDECESSOR
Phase 5 — Testing & Commissioning · Proposed baseline: Week 12 – Week 16
32 | 5.01 | Phase 5 — Testing & Commissioning | Installation inspection | All trailers | 4.09 |  |  | TBD | Not Started | 0% | TBC | QA/QC | TBC | TBC | Installation complete | — | Yes | Inspection and test plan to be issued during engineering. | TBD | PENDING PREDECESSOR
33 | 5.02 | Phase 5 — Testing & Commissioning | Cable and connection verification | All trailers | 5.01 |  |  | TBD | Not Started | 0% | TBC | Testing & Commissioning Lead | TBC | TBC | Installation inspection passed | — | No | Continuity, insulation and termination checks. | TBD | PENDING PREDECESSOR
34 | 5.03 | Phase 5 — Testing & Commissioning | Fire alarm system testing | All trailers | 5.02 |  |  | TBD | Not Started | 0% | TBC | Fire Alarm Engineer | TBC | TBC | Cable and connection verification complete | — | No | Test procedure to be approved before execution. | TBD | PENDING PREDECESSOR
35 | 5.04 | Phase 5 — Testing & Commissioning | Fire suppression system testing | All trailers | 5.02 |  |  | TBD | Not Started | 0% | TBC | Fire Suppression Engineer | TBC | TBC | Cable and connection verification complete | — | No | Test procedure to be approved before execution. | TBD | PENDING PREDECESSOR
36 | 5.05 | Phase 5 — Testing & Commissioning | Functional testing | All trailers | 5.03 |  |  | TBD | Not Started | 0% | TBC | Testing & Commissioning Lead | TBC | TBC | System testing complete | Requires stable power supply in all trailers | No | Cause-and-effect matrix to be produced during engineering. | TBD | PENDING PREDECESSOR
37 | 5.06 | Phase 5 — Testing & Commissioning | Integration testing | All trailers | 5.05 |  |  | TBD | Not Started | 0% | TBC | Fire & Life Safety Engineer | TBC | TBC | Functional testing complete | — | No | End-to-end verification across both recommended systems. | TBD | PENDING PREDECESSOR
38 | 5.07 | Phase 5 — Testing & Commissioning | Defect identification and punch list issue | All trailers | 5.06 |  |  | TBD | Not Started | 0% | TBC | QA/QC | TBC | TBC | Integration testing complete | — | No | Punch list to be logged in the Action Tracker. | TBD | PENDING PREDECESSOR
39 | 5.08 | Phase 5 — Testing & Commissioning | Rectification of defects | All trailers | 5.07 |  |  | TBD | Not Started | 0% | TBC | Main Contractor | TBC | TBC | Punch list issued | — | No | Rectification duration depends on defect volume — TBC. | TBD | PENDING PREDECESSOR
40 | 5.09 | Phase 5 — Testing & Commissioning | Retesting and verification | All trailers | 5.08 |  |  | TBD | Not Started | 0% | TBC | Testing & Commissioning Lead | TBC | TBC | Defects rectified | — | Yes | Retest scope limited to rectified items plus affected functions. | TBD | PENDING PREDECESSOR
Phase 6 — Handover · Proposed baseline: Week 16 – Week 18
41 | 6.01 | Phase 6 — Handover | Final inspection | All trailers | 5.09 |  |  | TBD | Not Started | 0% | TBC | QA/QC | TBC | TBC | Retesting complete | — | Yes | Joint inspection with Client Representative. | TBD | PENDING PREDECESSOR
42 | 6.02 | Phase 6 — Handover | Punch list closure | All trailers | 6.01 |  |  | TBD | Not Started | 0% | TBC | Main Contractor | TBC | TBC | Final inspection complete | — | No | Zero open critical items required for acceptance. | TBD | PENDING PREDECESSOR
43 | 6.03 | Phase 6 — Handover | As-built documentation | All trailers | 6.02 |  |  | TBD | Not Started | 0% | TBC | Fire System Specialist | TBC | TBC | Punch list closed | — | No | As-builts to reflect final installed configuration. | TBD | PENDING PREDECESSOR
44 | 6.04 | Phase 6 — Handover | Test reports compilation and submission | All trailers | 5.09 |  |  | TBD | Not Started | 0% | TBC | Testing & Commissioning Lead | TBC | TBC | Retesting complete | — | Yes | Signed test records for both recommended systems. | TBD | PENDING PREDECESSOR
45 | 6.05 | Phase 6 — Handover | Operation and Maintenance (O&M) documentation | All trailers | 6.03 |  |  | TBD | Not Started | 0% | TBC | Fire System Specialist | TBC | TBC | As-builts issued | — | Yes | O&M manuals and spare parts list. | TBD | PENDING PREDECESSOR
46 | 6.06 | Phase 6 — Handover | Operator and end-user training | All trailers | 6.05 |  |  | TBD | Not Started | 0% | TBC | Fire & Life Safety Engineer | TBC | TBC | O&M documentation issued | — | No | Trainee list and duration to be confirmed by the Project Owner. | TBD | PENDING PREDECESSOR
47 | 6.07 | Phase 6 — Handover | Final acceptance and client sign-off | All trailers | 6.06 |  |  | TBD | Not Started | 0% | TBC | Client Representative | TBC | TBC | Training complete + documentation accepted | — | Yes | Acceptance criteria to be agreed at kickoff. | TBD | PENDING PREDECESSOR
48 | 6.08 | Phase 6 — Handover | System handover to operations | All trailers | 6.07 |  |  | TBD | Not Started | 0% | TBC | Project Owner | TBC | TBC | Final acceptance obtained | — | Yes | Handover certificate and key/asset transfer. | TBD | PENDING PREDECESSOR
49 | 6.09 | Phase 6 — Handover | Project closeout | All trailers | 6.08 |  |  | TBD | Not Started | 0% | Kharsan Mujeb Al Ajmi | Project Manager | TBC | TBC | Handover complete | — | Yes | Final account, lessons learned and document archive. | TBD | PENDING PREDECESSOR
CRITICAL DEPENDENCIES & CONSTRAINTS — confirmed by the RC Vehicle Survey Report
Ref | Confirmed Constraint |  |  | Reason |  | Dependency |  |  | Required Action |  |  | Responsible Party |  |  | Target Resolution | Impact on Schedule |  |  | Classification
CD-01 | Trailer-2 power source is currently unavailable. |  |  | Partition works are still ongoing. |  | Completion of partition works + power availability confirmation. |  |  | Complete partition works in Trailer-2, then verify and energise the power source. |  |  | Civil / Partition Contractor (TBC) → Electrical Contractor (TBC) |  |  | TBD | Blocks activity 2.02 and 4.08, and gates functional testing (5.05) and Trailer-2 handover. |  |  | CONFIRMED CONSTRAINT (SURVEY)
CD-02 | Installation of Racks and Cabinets has not yet started in the available trailers. |  |  | Rack and cabinet works not yet commenced. |  | Completion and readiness sign-off of racks and cabinets (2.04 → 2.05). |  |  | Confirm scope, contractor and start date for racks and cabinets installation. |  |  | Main Contractor (TBC) |  |  | TBD | Gates activities 4.01, 4.04 and 4.07, and therefore the entire installation phase. |  |  | CONFIRMED CONSTRAINT (SURVEY)
Both constraints above are stated in the source survey report. Target resolution dates are TBD until confirmed by the Project Owner and the responsible contractors.
Formulas:
Days Remaining (auto) = IF([Planned Finish (enter date)]="","TBD",IF([Status]="Completed","Closed",[Planned Finish (enter date)]-TODAY()))

## 3. Gantt Chart
FIRE FIGHTING SYSTEM — NEW DC
Installation Schedule & Project Responsibility Tracker
Survey Date: 30-Jun-2026 ¦ PM: Kharsan Mujeb Al Ajmi ¦ [OFFICIAL LOGO — TO BE INSERTED]
PROPOSED BASELINE — DATES TO BE CONFIRMED. The timeline below is relative (Week 1 = project kickoff). It is NOT a calendar schedule. Proposed planning dates are preliminary and subject to confirmation by the Project Owner, PM, Contractor and relevant stakeholders.
LEGEND | [8 empty] | Preparation | [5 empty] | Site Readiness | [5 empty] | Engineering
[9 empty] | Installation | [5 empty] | Testing & Commissioning | [5 empty] | Handover
[9 empty] | Critical activity | [5 empty] | Trailer-2 power dependency
ID | WBS | Activity | Phase | Critical / Dependency | Prede- cessor | Baseline Wk Start | Baseline Wk Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Phase 1 — Project Preparation |  |  | Preparation | PHASE ENVELOPE | — | 1 | 2
1 | 1.01 | Project kickoff meeting and baseline agreement | Preparation | — | — | 1 | 1
2 | 1.02 | Site survey execution — RC Vehicle Survey | Preparation | — | —
3 | 1.03 | Review of RC Vehicle Survey Report dated 30-Jun-2026 | Preparation | — | 1.02 | 1 | 1
4 | 1.04 | Scope confirmation — Fire Alarm System and Fire Suppression System | Preparation | — | 1.03 | 1 | 2
5 | 1.05 | Confirmation of project stakeholders, owner and governance | Preparation | — | 1.01 | 1 | 2
6 | 1.06 | Site readiness verification walkdown | Preparation | — | 1.04 | 2 | 2
7 | 1.07 | Confirmation of trailer availability | Preparation | — | 1.06 | 2 | 2
8 | 1.08 | Confirmation of installation areas within trailers | Preparation | — | 1.07 | 2 | 2
Phase 2 — Civil / Site Readiness |  |  | Site Readiness | PHASE ENVELOPE | — | 1 | 6
9 | 2.01 | Completion of partition works | Site Readiness | CRITICAL | — | 1 | 4
10 | 2.02 | Power source availability verification and energisation | Site Readiness | T2 POWER | 2.01 | 4 | 5
11 | 2.03 | Verification of available installation areas | Site Readiness | — | 1.08 | 2 | 3
12 | 2.04 | Installation of Racks and Cabinets | Site Readiness | CRITICAL | 2.03 | 3 | 6
13 | 2.05 | Racks and Cabinets readiness confirmation / sign-off | Site Readiness | CRITICAL | 2.04 | 6 | 6
14 | 2.06 | Power availability verification — trailers other than Trailer-2 | Site Readiness | — | 1.07 | 2 | 3
15 | 2.07 | Access, HSE induction and work permit readiness | Site Readiness | — | 1.01 | 2 | 3
Phase 3 — Engineering & Material Readiness |  |  | Engineering | PHASE ENVELOPE | — | 2 | 8
16 | 3.01 | Fire suppression system design review | Engineering | — | 1.04 | 2 | 3
17 | 3.02 | Fire alarm system design review | Engineering | — | 1.04 | 2 | 3
18 | 3.03 | Equipment and material confirmation | Engineering | — | 3.01 | 3 | 4
19 | 3.04 | Shop drawing and technical submittal preparation | Engineering | — | 3.03 | 3 | 4
20 | 3.05 | Shop drawing and material approval | Engineering | CRITICAL | 3.04 | 5 | 5
21 | 3.06 | Procurement and purchase order release | Engineering | CRITICAL | 3.05 | 5 | 6
22 | 3.07 | Manufacturing, delivery to site and material inspection | Engineering | CRITICAL | 3.06 | 6 | 8
Phase 4 — Installation |  |  | Installation | PHASE ENVELOPE | — | 8 | 12
23 | 4.01 | Fire alarm system installation — containment and cabling | Installation | CRITICAL | 3.07 | 8 | 9
24 | 4.02 | Fire detection devices installation | Installation | — | 4.01 | 9 | 10
25 | 4.03 | Fire alarm control and monitoring equipment installation | Installation | — | 4.01 | 9 | 10
26 | 4.04 | Fire suppression system installation — mounting and supports | Installation | CRITICAL | 3.07 | 8 | 10
27 | 4.05 | Suppression equipment installation | Installation | — | 4.04 | 10 | 11
28 | 4.06 | Piping / tubing and associated components installation (where applicable) | Installation | — | 4.05 | 10 | 11
29 | 4.07 | Interfaces with racks and cabinets | Installation | CRITICAL | 2.05 | 11 | 11
30 | 4.08 | Power and control connections | Installation | T2 POWER | 2.02 | 11 | 12
31 | 4.09 | System integration — fire alarm and fire suppression | Installation | CRITICAL | 4.08 | 12 | 12
Phase 5 — Testing & Commissioning |  |  | Testing | PHASE ENVELOPE | — | 12 | 16
32 | 5.01 | Installation inspection | Testing | — | 4.09 | 12 | 12
33 | 5.02 | Cable and connection verification | Testing | — | 5.01 | 12 | 12
34 | 5.03 | Fire alarm system testing | Testing | — | 5.02 | 13 | 13
35 | 5.04 | Fire suppression system testing | Testing | — | 5.02 | 13 | 13
36 | 5.05 | Functional testing | Testing | CRITICAL | 5.03 | 14 | 14
37 | 5.06 | Integration testing | Testing | — | 5.05 | 14 | 14
38 | 5.07 | Defect identification and punch list issue | Testing | — | 5.06 | 15 | 15
39 | 5.08 | Rectification of defects | Testing | — | 5.07 | 15 | 15
40 | 5.09 | Retesting and verification | Testing | — | 5.08 | 16 | 16
Phase 6 — Handover |  |  | Handover | PHASE ENVELOPE | — | 16 | 18
41 | 6.01 | Final inspection | Handover | — | 5.09 | 16 | 16
42 | 6.02 | Punch list closure | Handover | — | 6.01 | 16 | 16
43 | 6.03 | As-built documentation | Handover | — | 6.02 | 16 | 17
44 | 6.04 | Test reports compilation and submission | Handover | — | 5.09 | 17 | 17
45 | 6.05 | Operation and Maintenance (O&M) documentation | Handover | — | 6.03 | 17 | 17
46 | 6.06 | Operator and end-user training | Handover | — | 6.05 | 17 | 17
47 | 6.07 | Final acceptance and client sign-off | Handover | CRITICAL | 6.06 | 18 | 18
48 | 6.08 | System handover to operations | Handover | CRITICAL | 6.07 | 18 | 18
49 | 6.09 | Project closeout | Handover | — | 6.08 | 18 | 18
PLANNED PROJECT COMPLETION — HANDOVER & CLOSEOUT (proposed) | [5 empty] | 18 | 18 | bar: 1 to Trailer-2 power dependency 18
Dependencies are shown by the Predecessor column; each activity may only start once its predecessor is complete. Activities marked CRITICAL sit on the critical path. Activities marked T2 POWER cannot proceed until partition works in Trailer-2 are complete and the power source is confirmed available.

## 4. Responsibility Matrix
FIRE FIGHTING SYSTEM — NEW DC
Installation Schedule & Project Responsibility Tracker
Survey Date: 30-Jun-2026 ¦ PM: Kharsan Mujeb Al Ajmi ¦ [OFFICIAL LOGO — TO BE INSERTED]
The only person identified in the source survey report is Kharsan Mujeb Al Ajmi (Project Manager). All other names are marked TBC — To Be Confirmed. Names and contact details are editable fields for the project team to complete; no names have been assumed.
PROJECT GOVERNANCE — editable
Project Owner | TBC |  | Enter the confirmed name here once appointed.
Project Manager | Kharsan Mujeb Al Ajmi |  | Confirmed by the source survey report.
Main Contractor | TBC |  | Enter the confirmed name here once appointed.
Fire System Contractor | TBC |  | Enter the confirmed name here once appointed.
Client Representative | TBC |  | Enter the confirmed name here once appointed.
QA/QC | TBC |  | Enter the confirmed name here once appointed.
HSE | TBC |  | Enter the confirmed name here once appointed.
PROJECT RESPONSIBILITY MATRIX
Responsibility Area | Name | Role | Organization / Contractor | Responsibility | Contact | Status
Project Ownership | TBC | Project Owner | TBC | Overall accountability, funding, acceptance and handover authority. | TBC | Not Started
Project Management | Kharsan Mujeb Al Ajmi | Project Manager | TBC | Day-to-day management, schedule, reporting and stakeholder coordination. | TBC | In Progress
Fire & Life Safety | TBC | Fire & Life Safety Engineer | TBC | Design compliance, integration and life-safety assurance. | TBC | Not Started
Fire Alarm Engineering | TBC | Fire Alarm Engineer | TBC | Fire alarm design review, installation supervision and testing. | TBC | Not Started
Fire Suppression Engineering | TBC | Fire Suppression Engineer | TBC | Fire suppression design review, installation supervision and testing. | TBC | Not Started
Site Supervision | TBC | Site Supervisor | TBC | Daily site control, work fronts, coordination between trades. | TBC | Not Started
Main Works | TBC | Main Contractor | TBC | Overall construction delivery including racks and cabinets installation. | TBC | Not Started
Fire System Delivery | TBC | Fire System Specialist | TBC | Supply and installation of the recommended fire alarm and suppression systems. | TBC | Not Started
Electrical Works | TBC | Electrical Contractor | TBC | Power supply, energisation and power/control connections. | TBC | Not Started
Civil / Partition Works | TBC | Civil / Partition Contractor | TBC | Partition works in Trailer-2 — currently ongoing per survey. | TBC | In Progress
Quality Assurance | TBC | QA/QC | TBC | Inspection, ITP execution, punch list management and sign-off. | TBC | Not Started
Health, Safety & Environment | TBC | HSE | TBC | Permits, inductions, risk assessments and site safety compliance. | TBC | Not Started
Testing & Commissioning | TBC | Testing & Commissioning Lead | TBC | Test procedures, functional and integration testing, test records. | TBC | Not Started
Client Interface | TBC | Client Representative | TBC | Approvals, witnessing, final acceptance and handover receipt. | TBC | Not Started
TBC — To Be Confirmed. Shaded cells are editable fields for the project team.

## 5. Action Tracker
FIRE FIGHTING SYSTEM — NEW DC
Installation Schedule & Project Responsibility Tracker
Survey Date: 30-Jun-2026 ¦ PM: Kharsan Mujeb Al Ajmi ¦ [OFFICIAL LOGO — TO BE INSERTED]
MANAGEMENT ACTION TRACKER — actions ordered by their ability to delay installation. Critical path sequence: complete partition works in Trailer-2 → confirm power availability → complete racks and cabinets → confirm site readiness → release installation activities. Due dates are TBD until the baseline is confirmed.
Action ID | Required Action | Reason | Responsible | Due Date | Priority | Status | Escalation Required | Remarks
A01 | Complete partition works in Trailer-2 | Survey confirms partition works are still ongoing, which is blocking the power source. | Civil / Partition Contractor (TBC) | TBD | Critical | In Progress | Yes | CRITICAL PATH — first link in the Trailer-2 readiness chain.
A02 | Confirm power availability in Trailer-2 once partitions are complete | Survey confirms the Trailer-2 power source is currently unavailable. | Electrical Contractor (TBC) | TBD | Critical | Blocked | Yes | CRITICAL PATH — gates power and control connections and functional testing.
A03 | Start and complete installation of Racks and Cabinets | Survey confirms rack and cabinet installation has not yet started in the available trailers. | Main Contractor (TBC) | TBD | Critical | Not Started | Yes | CRITICAL PATH — gates all rack/cabinet-interfacing fire system works.
A04 | Confirm overall site readiness and release installation work fronts | Installation cannot be released until partitions, power and racks/cabinets are confirmed ready. | Project Manager — Kharsan Mujeb Al Ajmi | TBD | Critical | Not Started | Yes | Sequence: A01 → A02 → A03 → A04 → release Phase 4.
A05 | Nominate the Project Owner and confirm the governance structure | No project owner is identified in the source document; approvals cannot be routed. | Project Manager — Kharsan Mujeb Al Ajmi | TBD | High | Not Started | Yes | Required before any approval-gated activity can complete.
A06 | Appoint the Main Contractor and Fire System Contractor | No contractor is named in the source document. | Project Owner (TBC) | TBD | High | Not Started | Yes | Required to resource Phases 2 to 6.
A07 | Confirm fire alarm and fire suppression design basis and equipment selection | The survey recommends both systems but does not specify equipment types. | Fire & Life Safety Engineer (TBC) | TBD | High | Not Started | No | Equipment types to be confirmed during engineering/design.
A08 | Establish and approve the project baseline dates | The source document provides no start, duration or completion dates. | Project Manager — Kharsan Mujeb Al Ajmi | TBD | High | Not Started | No | Converts the proposed relative baseline into confirmed calendar dates.
A09 | Confirm procurement lead times for the approved materials | Long-lead items may govern the installation start date. | Main Contractor (TBC) | TBD | Medium | Not Started | No | Feeds milestone M06 — Materials Available on Site.
A10 | Confirm the power availability status of all trailers other than Trailer-2 | The survey confirms the constraint for Trailer-2 only; other trailers are not addressed. | Electrical Contractor (TBC) | TBD | Medium | Not Started | No | Closes an open information gap in the source document.
A11 | Establish the permit-to-work and HSE regime for trailer works | Work cannot commence without access and permit readiness. | HSE (TBC) | TBD | Medium | Not Started | No | Prerequisite for all site work fronts.
A12 | Agree the approval authority and review turnaround for submittals | Approval route is undefined, which puts the engineering gate at risk. | Client Representative (TBC) | TBD | Medium | Not Started | No | Feeds milestone M05 — Engineering Approved.
Actions A01–A04 form the critical path to releasing installation. Shaded Due Date cells are editable.

## 6. Risk Register
FIRE FIGHTING SYSTEM — NEW DC
Installation Schedule & Project Responsibility Tracker
Survey Date: 30-Jun-2026 ¦ PM: Kharsan Mujeb Al Ajmi ¦ [OFFICIAL LOGO — TO BE INSERTED]
Risks R01 and R02 are the constraints explicitly recorded in the source survey report. All remaining entries are standard project-planning risks and are labelled “Planning Risk — To Be Validated”. Probability, Severity and Status are drop-down lists; the Risk Rating column calculates automatically.
Risk ID | Risk | Cause | Impact | Probability | Severity | Mitigation | Owner | Target Date | Status | Risk Rating (auto) | Classification
R01 | Trailer-2 power source remains unavailable | Partition works in Trailer-2 are still ongoing (confirmed by survey). | Power and control connections, functional testing and Trailer-2 handover cannot proceed. | High | High | Expedite partition works; agree a firm completion date; confirm energisation plan; consider a temporary certified supply if approved. | Civil / Partition Contractor (TBC) | TBD | Open | CRITICAL | Source-confirmed constraint
R02 | Racks and Cabinets installation has not started | Rack and cabinet works not yet commenced in the available trailers (confirmed by survey). | All rack/cabinet-interfacing fire alarm and suppression activities are gated; installation start slips. | High | High | Confirm rack/cabinet scope, contractor and start date; sequence rack installation ahead of fire system works. | Main Contractor (TBC) | TBD | Open | CRITICAL | Source-confirmed constraint
R03 | No confirmed project baseline dates | The source document provides no start, duration or completion dates. | Progress cannot be measured; delay cannot be evidenced; no contractual float visibility. | High | Medium | Convert the proposed relative baseline into calendar dates at kickoff and freeze as Version 1.0. | Project Manager — Kharsan Mujeb Al Ajmi | TBD | Open | HIGH | Planning Risk — To Be Validated
R04 | Project Owner and contractors not yet appointed | No owner or contractor is identified in the source document. | Approvals stall; no accountable party for the critical path actions. | High | Medium | Nominate the Project Owner and award the main and fire system packages before Phase 3 approvals. | Project Owner (TBC) | TBD | Open | HIGH | Planning Risk — To Be Validated
R05 | Equipment selection not yet defined | The survey recommends the systems but does not specify equipment types. | Procurement cannot start; lead times remain unknown; installation start date unreliable. | Medium | High | Complete design reviews and freeze the material schedule before releasing purchase orders. | Fire & Life Safety Engineer (TBC) | TBD | Open | HIGH | Planning Risk — To Be Validated
R06 | Long procurement lead times govern the critical path | Fire suppression equipment can carry extended manufacturing lead times. | Installation start is deferred; overall completion date slips. | Medium | High | Obtain lead-time confirmation at quotation stage; pre-order long-lead items after approval. | Main Contractor (TBC) | TBD | Open | HIGH | Planning Risk — To Be Validated
R07 | Approval turnaround for submittals is undefined | No approval authority or review duration has been agreed. | Engineering gate slips and delays procurement release. | Medium | Medium | Agree the approval matrix and a maximum review turnaround at kickoff. | Client Representative (TBC) | TBD | Open | MEDIUM | Planning Risk — To Be Validated
R08 | Trade congestion inside the trailers | Civil, electrical, rack and fire system trades share a confined trailer envelope. | Work front conflicts, rework and reduced productivity. | Medium | Medium | Produce a sequenced work-front plan and a shared trailer access schedule. | Site Supervisor (TBC) | TBD | Open | MEDIUM | Planning Risk — To Be Validated
R09 | Power availability of remaining trailers unverified | The survey addresses the Trailer-2 power constraint only. | A further power constraint may emerge late and block additional work fronts. | Medium | Medium | Verify and record the power status of every trailer before releasing installation. | Electrical Contractor (TBC) | TBD | Open | MEDIUM | Planning Risk — To Be Validated
R10 | Interface between fire systems and DC racks not yet defined | Rack layout and installation areas are not yet fixed. | Detection coverage and suppression arrangement may require redesign after rack installation. | Medium | Medium | Freeze the rack layout before finalising detection and suppression shop drawings. | Fire & Life Safety Engineer (TBC) | TBD | Open | MEDIUM | Planning Risk — To Be Validated
Risk Rating is derived from Probability × Severity: High/High = CRITICAL; High/Medium = HIGH; Low/Low = LOW; all other combinations = MEDIUM.

## 7. Document Control
FIRE FIGHTING SYSTEM — NEW DC
Installation Schedule & Project Responsibility Tracker
Survey Date: 30-Jun-2026 ¦ PM: Kharsan Mujeb Al Ajmi ¦ [OFFICIAL LOGO — TO BE INSERTED]
DOCUMENT CONTROL
Document Title | Fire Fighting System Installation Schedule
Project | New DC
Asset / Location | Mobile / Trailer-based DC
Source Document | RC Vehicle Survey Report – Fire Fighting System for New DC
Survey Date | 30-Jun-2026
Project Manager | Kharsan Mujeb Al Ajmi
Version | 0.1
Status | Preliminary — Planning Baseline
Prepared By | TBC
Reviewed By | TBC
Approved By | TBC
Last Updated | TBC
REVISION HISTORY
Version | Description of Change | Date | Prepared By | Reviewed By | Approved By
0.1 | Initial preliminary planning baseline prepared from the RC Vehicle Survey Report dated 30-Jun-2026. All dates proposed and subject to confirmation. | TBC | TBC | TBC | TBC
SOURCE TRACEABILITY — what is confirmed and what is proposed
Item | Value / Statement | Classification | Source | Sheet Reference | Note
Project | Fire Fighting System for New DC | CONFIRMED | RC Vehicle Survey Report – Fire Fighting System for New DC | All sheets | Stated in the survey report.
Location / Asset | Mobile / Trailer-based DC | CONFIRMED | RC Vehicle Survey Report – Fire Fighting System for New DC | All sheets | Stated in the survey report.
Survey Date | 30-Jun-2026 | CONFIRMED | RC Vehicle Survey Report – Fire Fighting System for New DC | All sheets | Stated in the survey report.
Project Manager | Kharsan Mujeb Al Ajmi | CONFIRMED | RC Vehicle Survey Report – Fire Fighting System for New DC | All sheets | The only person named in the source.
Site condition | Installation of Racks and Cabinets has not yet started in the available trailers. | CONFIRMED | RC Vehicle Survey Report – Fire Fighting System for New DC | 2. Master Schedule (2.04) / CD-02 | Drives the rack and cabinet readiness dependency.
Site condition | The power source in Trailer-2 is currently unavailable because partition works are still ongoing. | CONFIRMED | RC Vehicle Survey Report – Fire Fighting System for New DC | 2. Master Schedule (2.02) / CD-01 | Drives the Trailer-2 power dependency.
Recommended system | Fire Alarm System | CONFIRMED | RC Vehicle Survey Report – Fire Fighting System for New DC | 2. Master Schedule (Phase 3–5) | Recommended by the survey.
Recommended system | Fire Suppression System | CONFIRMED | RC Vehicle Survey Report – Fire Fighting System for New DC | 2. Master Schedule (Phase 3–5) | Recommended by the survey.
Start / finish dates | Not stated in the source | PROPOSED / TBD | Not available | All sheets | Relative Week 1–18 baseline only; calendar dates TBD.
Overall duration | Not stated in the source | PROPOSED / TBD | Not available | 3. Gantt Chart | 18-week proposed baseline, subject to confirmation.
Project Owner / contractors | Not stated in the source | TBC | Not available | 4. Responsibility Matrix | No names assumed.
Equipment types | Not stated in the source | TBC | Not available | 2. Master Schedule (Phase 3–4) | To be confirmed during engineering/design.
Confidential — Project Planning Document. Prepared based on the RC Vehicle Survey Report dated 30-Jun-2026. Version 0.1 — Preliminary Planning Baseline. Last updated: TBC.